## Document details
Ref | PJM_T02_Project_Estimation sheet
Mailing list | Name | Company | Cc | Name | Company
Object
Client/Prospect
Project
Manager
Project Manager
Confidentaility | Internal
History
Date | Version | Update description | Author | Validator | Status

## Project Items
Client/Prospect |  | Date:
Project
Manager
Project Manager
[9 empty] | Front End | [10 empty] | Back End | [19 empty] | Functional Testing
Gap référence | Function | Sub-Function | Description | Gap | Assumptions and Comments | Type | Phase / Iteration | Classification | Angular Screen |  |  | Native Angular Components |  |  |  | Components Integration in UI Studio |  |  |  | Non Angular Screen (SWING) |  |  |  | Non Angular Screen (GWT) |  |  |  | Reports |  |  | Process |  |  | Configuration |  |  | Service/Activity |  |  | F° Testing |  |  | Total Dev | F° Testing | STD | STD_MKT | SPEC | With Risk
| Function |  | Description | Gap | Assumptions and Comments | Type | Phasing |  | S | A | D | S | A | D | C | S | A | D | C | S | A | D | C | S | A | D | C | S | A | C | S | A | C | S | A | C | S | A | C | S | A | D |  |  | STD | STD_MKT | SPEC | With Risk
| Function | Sub-Function | Description | Gap | Assumptions and Comments | Type | Phasing | Classification | 60 | 12 | 0 | 1 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 22 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 11 | 1 | 0 | 0 | 0 | 361.82 | 0 | #REF! | #REF! | #REF! | 933.4956
WP01 Carga manual de COMPRA - DVP / FOP - GC y LC | >>Update the current manual input screen in order to manage international settlement operations ==> additional fields should be added in case of international settlement. III. Tipo de intrumento: ( drop-down menu must be placed to take the type of instrument) a. Bloomberg Ticker b. Common c. Cusip d. ISIN e. Local Number f. Sedol g. Ticket X. Tipo de Mercado: (A drop-down menu must be placed to take the type of market) a) DTC b) EUROCLEAR c) CLEARSTREM d) FRB e) NIB f) Local Market XI. Contrapartes : a) Identificación del tipo de Broker: Participante en DTC (All DTC participants or a search by their respective identification must be displayed) b) Tipo de Clearer : Participante en DTC (All DTC participants or a search by their respective identification must be displayed) ==>Gaps: 3 new fields should be added with 3 new WS | Yes |  | X | ok | 1 Simple Screen 3 WS BE |  |  | Angular Screen S: 1; Service/Activity S: 3 | 3.575 | 0 | #REF! | #REF! | #REF! | 5.8094
| 1-a new screen to be added in order to manage the manual input of new issuance of a new security issued on the primary market -Referencia cliente (En: Client Reference) -Deposito (En:Custodian): a)Deceval b)DCV -Cuenta (En: Client Sec Account) ==> WS to get the list of accounts -Emisor (En: Issuer) (List of all issuers in the Colombian market) ==> Ws to get the list of Issuers -Monto de la inversión (En: Investment Amount) -Nemotecnico (En: Mnemonic code/Short Code) -Fecha de emisión (En: Issue date) -Fecha de vencimiento (En: Maturity Date) -Periodicidad (En: Periodicity): a)-Mensual vencido b)-Trimestre vencido c)-Semestre vencido d)-Periodo vencido -Tipo de Tasa (En: Interest Rate Type): a)Efectiva b)Nominal c)IPC d)DTF e)IBR -Spread/Tasa (En: Spread) -Base (Base pueder 360 ó 365) -Semana de pago (En: Payment Week) : a)Inicial b)Final -Mercado (En: Market) (OTC o BVC) -ISIN ==> Gaps: -new screen to input the new security instruction with fields -new Ws to retreive the list of issuers -new WS to save the instruction | Yes |  | X | OK | NA | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0
WP03 Carga manual de REPO PASIVO BanRep | 1-New screen to manually input a Repo operation with the possibility to manage 2 sub operations: a- a new Intraday Repo operation with standard fields b- an extension of an existing repo operation ==>Gaps: 1-new dedicated screen 2-new field to indicate whether it's an intrady repo or an extension and if extension additional fields will be displayed. 3-a new WS to retreive the Intraday repo oeprations to be extended 4- a new WS to save the new operation (new Intraday or Extension) | Yes | X |  | OK | 1New simple screen to input the original Repo 1 New Simple Screen to fetch Repo Oeprations 1 New Simple Screen to display result 1 New Simple Screen to Extend (Clone) the original Operation 1 WS to save the operation 1 WS to cancel a new operation |  |  | Angular Screen S: 4; Service/Activity S: 6 | 8.9 | 0 | 0 | 0 | 0 | 14.4625
WP07 Manual Cargue de garantias | 1-New Screen to input a new instruction of Block/Unblock with the following fields: -Referencia cliente(En: client Reference) -Cuenta de cliente (En: Client Sec Account) ==> WS to retreive the Client Account ==> No Gap -Tipo de operación (Constitución / Liberación) (En: Transaction Type: Block / Unblock)) -Numero de Folio de regreso. -Fecha de regreso (En: maturity date) -Valor Nominal Garantia (En: Quantity) -ISIN ==> WS to retreive the list of ISINs ==> No Gap -Emisión -Cuenta Deposito (En: Nostro Account) ==> WS to retreive the Nostro Account ==> No Gap 2-New Screen to monitor Block/Unblock Instructions ==> Gaps: -1 new input screen -1 new monitoring screen -1 new WS to save the Block/Unblock instruction -1 new WS to retreive the Block/Unblock instructions for monitoring reason. -1 new Ws to Cancel a pending Instruction | Yes | X |  | Ok | 1 new input screen 1 new monitoring screen 1 new WS to save the Block/Unblock instruction 1 new WS to retreive the Block/Unblock instructions for monitoring reason. 1 new Ws to Cancel a pending Instruction |  |  | Angular Screen S: 4; Service/Activity S: 6 | 8.9 | 0 | 0 | 0 | 0 | 14.4625
WP08 Cargas Masivas de instrucciones de todas las operaciones en formato XLS, XLSX, CSV, TXT | Possibility to load all type of operations using all these format: XLS, XLSX, CSV and TXT -OTC, -International Settlement Instruction, -Repo Intraday, -Repo Extension -Block/Unblock instruction -New Issuance (NA) | Yes | X |  | OK | 1 Simple upload screen 1 WS to upload (Complex) : 5 templates in 4 formats |  |  | Angular Screen S: 1; Native Angular Components S: 1; Reports A: 20; Service/Activity A: 1 | 55.175 | 0 | 0 | 0 | 0 | 89.6594
WP09 Anuncios, Recálculos, Abonos - Pagos en efectivo / Pagos en especie | CA Entitlement consultation screen ==> GAP: update STD WS to include more information in the response to be displayed (around 5 fields) | Yes | X |  | OK | 1 search result simple screen 1 WS average |  |  | Angular Screen S: 2; Service/Activity A: 2 | 7.75 | 0 | 0 | 0 | 0 | 12.5938
WP12 Esquema Maker & Checker | A new requirement in order to apply 6 Eyes instead of 4 Eyes ==> new WS to manage the validation on 3 level | Yes | X |  | OK | 1 average screen 1 WS average | [36 empty] | 5 | 0 | 0 | 0 | 0 | 8.125 | bar: Angular Screen A; Service/Activity A
WP13 Posición de Activos a la fecha actual y/o fechas pasadas por portafolio / ISIN - GC - LC (Cash + Sec. + Funds) | Screen to consult Security and Cash Positions and be able to export it in Excel, CSV and TXT ==> GAP: add the possibility to export in CSV and TXT | Yes | X |  | OK | 1 simple screen 1 average WS |  |  | Angular Screen S: 1; Reports A: 2; Service/Activity S: 1; Service/Activity C: 1 | 12.815 | 0 | 0 | 0 | 0 | 20.8244
WP 14 Operaciones instruidas (LC + GC) Filtros: por estado, por contraparte, SD, Portafolio. | Screen to consult instructions and be able to export it in Excel, CSV and TXT ==> GAP: 1-add the possibility to export in CSV and TXT 2-modify the existing WS used to retreive the instructions in order to add more information (less than 5) | Yes | X |  | OK | 1 average screen 1 average WS 1 WS simple |  |  | Angular Screen S: 2; Service/Activity S: 1; Service/Activity A: 1 | 5.65 | 0 | 0 | 0 | 0 | 9.1813
WP15 Detalle de las condiciones de la operación en instrucciones enviadas. | Covered by the WP14 | No | X |  | OK | [37 empty] | 0 | 0 | 0 | 0 | 0 | 0
WP 16 Pago de dividendos por fecha / rango de fechas / Val. esperados / recaudados (Cash + Sec. + OMM + Funds) | A screen to display the CA payments with the posibility to filter by date a range of dates, amount, ISIN/CUSIP, Event Reference, Election Start Date, accounts. Currently the screen exists but additional fields are requested: Fecha de pago por rangos (En: Payment date by ranks) Valores de pago (En: Payment values) Valor de intereses (En: Interest value ) Valor de capital (En: Capital value ) Valor Neto (En: Net Worth ) Valor Bruto (En: Gross Value) Cuenta cash (En: Cash account) Cuenta de titulos (En: Title account) Valor por acción (En: Value per share ) Porentaje de retención (En: Retention porentage) ==> Gaps : some fields to be added in Megara | Yes | X |  | OK | 3 Simple Screens (Search Input, Search Result, View) 1 WS simple |  |  | Angular Screen S: 3; Service/Activity S: 1 | 3.525 | 0 | 0 | 0 | 0 | 5.7281
WP 17 Información Proxy Voting - Agendas de Asambleas | A screen to display the Proxy voting agnedas with possibility to apply filters: •Fecha del Evento (Event Date) •Record date •Exdate •Tipo de Evento (Obligatorio, Voluntario, Choose) | Yes | X |  | OK | 1 search screen simple 1 average screen to dispplay the calendar 2 WS simple |  |  | Angular Screen S: 1; Angular Screen A: 1; Service/Activity S: 2 | 4.675 | 0 | 0 | 0 | 0 | 7.5969
WP 18 Proxy Voting-Eventos Voluntarios - Instrucciones recibidas y transmitidas | A screen to display the instructions related to proxy voting with the possibility of to apply different filers. •Referencia de la instrucción (En: Instruction Ref) •Cuenta (En: Client Sec Account) •Nombre (en: Number) •Referencia del Evento (En: CA Reference) •Estado (Pendiente, con voto) (En: Proxy Voting Status) •Fecha de pago del evento (En: Event Payment Date) •Tipo de Evento (Asamblea, Pago de Dividendos con opción, ofertas) (En: Event Type) •Dead line envío instrucción (En: Event deadline) ==> Gap: a new screen WS to retreive the Instructions | Yes | X |  | OK | 1 average screen search 1 average result 1 simple view screen 1 WS to retreive the infos from BE |  |  | Angular Screen A: 3; Service/Activity S: 3 | 8.7 | 0 | 0 | 0 | 0 | 14.1375
WP 19 Proxy Voting - Resultados de las Votaciones | a screen to display the result of a Prxy voting events. •Referencia de la instrucción (EN: Instruction ref) •Cuenta (En: Client Sec Account) •Nombre (En;Number) •Referencia del Evento (En: CA reference) •Fecha de pago del evento (En: Event payment date) •Campo con el resultado de la votaciones (En: result of the vote) ==> Gap: a WS to retreive the result of Proxy voting events | Yes | X |  | OK | 1 average screen search 1 average result 1 simple view screen 1 WS to retreive the infos from BE |  |  | Angular Screen A: 3 | 6 | 0 | 0 | 0 | 0 | 9.75
WP20 Reportes Operacionales | 3 Reports to be generated in the following format : PDF, XLS, XLSX, CSV, TXT and with the possibility to apply different filters 1-Extracto de Securities por fecha/ rango de fechas, por portafolios, por ISIN ==> A security position report with the possibility to apply a filter by date, range of date, account or ISIN. 2-Extractos de Cash por fecha / rango de fechas y portafolios==> A cash position and movement report with the possibility to apply a filter by date, range of date or account. 3-Operaciones instruidas por fecha / rango de fechas / x portafolio / x rango de portafolios (Cash + Sec. + Funds) ==> A report about instructed instructions with the possibility to apply a filter by date, range of date or account ==>Gap: 1- although the extracts are managed by current WS by we need to amend them in order to add more fields 2-3WS to generate the 3 reports with the selected format (the format can be passed as parameter) | Yes | X |  | OK | For each report in 5 formats (to be multiplied by 3) 1 average screen 1 complex WS 5 reports simples |  |  | Angular Screen S: 1; Native Angular Components A: 1; Reports S: 15; Service/Activity S: 2 | 22.675 | 0 | 0 | 0 | 0 | 36.8469
WP21 Reportes COACs | 3 Reports to be generated in the following format : PDF, XLS, XLSX, CSV, TXT and with the possibility to apply different filters 1.CoAcs por fecha - Rango de Fechas/ Val. esperados / fecha Val. recaudos (Cash + Sec. + Funds) ==> a report of the CA payments with the posibility to filter by daten a range of dates, amount and accounts. 2.Proxy Voting - Instrucciones recibidas y transmitidas ==> a report of the instructions related to proxy voting with the possibility of to apply different filers 3.Proxy Voting - Resultados de las Votaciones ==> a report to include the result of a Prxy voting events. ==>Gap: assuming that we have already services (WP18, WP19 andWP16) then we will need 3 WS to generate the report with the selected format (the format can be passed as parameter) | Yes | X |  | OK | For each report in 5 formats (to be multiplied by 3) 1 average screen 1 complex WS 5 reports simples |  |  | Angular Screen S: 1; Native Angular Components A: 1; Reports S: 15; Service/Activity S: 10 | 29.875 | 0 | 0 | 0 | 0 | 48.5469
General Requirement | Translation to Spanish | Yes | X |  | Ok | [37 empty] | 1.775 | 0 | 0 | 0 | 0 | 2.8844 | bar: Angular Screen S; Service/Activity S
WP35 Estado CONSOLIDADO de las instrucciones de Operación - LC - GC | >>> 9 Dashbaord to be added (El dashborad must be composed of the different widgets for each resulting infroma, the screen must allow to add and remove the widgets depending on the need of the user.) 1. Lista de transacciones pendientes de validación. | Yes |  |  |  | 1 screen SuperComplex 1 search screen simple 9 simple screen/widets |  |  | Angular Screen S: 10; Native Angular Components C: 1; Service/Activity S: 10 | 39.65 | 0 | 0 | 0 | 0 | 64.4313
| 2. Lista de transacciones incompletas. | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 3. Lista de transacciones canceladas. | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 4. Lista de transacciones cumplidas rango de fechas | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 5. Lista de transacciones incumplidas. | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 6. Lista de operaciones simultaneas por rango de fechas | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 7. Operaciones pendientes de cumplimiento. | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 8. Operaciones en el exterior BONY y EUROCLEAR o cualquier otro proveedor en mercados extranjeros | Yes | [41 empty] | 0 | 0 | 0 | 0 | 0
| 9. Operaciones con cumplimiento local. DCV y DECEVAL | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
WP36 Estado CONSOLIDADO de las instrucciones de CoACs - LC – GC | 6 CA Widgets & 9 Proxy Voting Widget: CA: 1.Listado de eventos corporativos aplicables nuevos | No |  |  |  | 3 Simple screens for each dashbaord 15 simple widgets |  |  | Angular Screen S: 15; Native Angular Components A: 1; Service/Activity S: 15 | 31.325 | 0 | 0 | 0 | 0 | 50.9031
| CA: 2.Lista de instrucciones a la espera de validación | No | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| CA: 3.Lista de instrucciones para eventos Voluntarios | No | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| CA: 4.Lista de eventos pendientes por instruir | No | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| CA: 5.Lista de instrucciones rechazas | No | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| CA: 6.Lista de instrucciones aceptadas | No | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Proxy Voting: 1.Listado de eventos corporativos aplicables nuevos para Votacion | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Proxy Voting: 2.Lista de instrucciones a la espera de validación | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Proxy Voting: 3.Lista de instrucciones para Asambleas | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Proxy Voting: 4.Lista de votos pendientes por instruir | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Proxy Voting: 5.Lista de instrucciones rechazas en Asamblea | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Proxy Voting: 6.Lista de instrucciones aceptadas en Asamblea | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Proxy Voting-Resultados: 1.Listado de eventos corporativos aplicables nuevos para Votación | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Proxy Voting-Resultados: 2.Listado de resultados de votaciones ya ejecutadas | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Proxy Voting-Resultados: 3.Listado de votación por cada uno de los resultados | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
WP 37 Estado CONSOLIDADO posicion Cash, x portafolio | 4 widgets related to security positions: 1.Listado de posición disponible | No |  |  |  | 2 simple screens for each dashbaord (Cash and Sec) 7 Simple widgets |  |  | Angular Screen S: 9; Service/Activity S: 9 | 15.975 | 0 | 0 | 0 | 0 | 25.9594
| 2.Listado de posición bloqueada | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 3.Listado de posición por depósitos (DCV, DECEVAL, BONY, Euroclear o cualquier otro proveedor en mercados extranjeros) | Yes | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 4.Listado de posiciones pendientes | No | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 3 widgets related to cash positions: 1.Listado de saldos en cuentas a un rango de fechas. | No | [40 empty] | 0 | 0
| 2.Listado de movimientos por cuenta por un rango de fechas | No | [40 empty] | 0 | 0
| 3.Listado de movimientos pendientes | No | [40 empty] | 0 | 0
WP40 Informe CONSOLIDADO de las instrucciones de Operación - LC - GC | Report PDF/EXCEL covering the Widgets defined in WP35 | Yes |  |  |  | 2 Report Complex 2WS simple |  |  | Angular Screen A: 1; Reports C: 2; Service/Activity A: 2 | 23.36 | 0
WP41 Informe CONSOLIDADO de las instrucciones de CoACs - LC – GC | Report PDF/EXCEL covering the Widgets defined in WP36 | Yes |  |  |  | 2 Report Complex 2WS simple |  |  | Angular Screen A: 1; Reports C: 2; Service/Activity A: 2 | 23.36 | 0
WP 46 Informe CONSOLIDADO posicion Cash, x portafolio | Report PDF/EXCEL covering the Widgets defined in WP36 | Yes |  |  |  | 2 Report Complex 2WS simple |  |  | Angular Screen A: 2; Reports C: 2; Service/Activity A: 2 | 25.36 | 0
WP42 Cargas Masivas de archivos en formato XLS, XLSX, CSV, TXT | 1 New screen to upload files (XLS, XLSX, CSV & TXT) by the admin to be consulted by the clients with the possibility to define a validity date and the permissions to access these files (by Client ALL clients). 1 New screen to consult the uploaded and still valid files | Yes |  |  |  | 1 Simple Upload screen 1 simple Search Input consultation screen 1 simple search result consultation screen 1 simple Edit screen 1 WS related to the edit 1 WS related to the uplaod 1 New simple screen to see the documents 1 WS download |  |  | Angular Screen S: 4; Native Angular Components D: 1; Service/Activity S: 4 | 17.8 | 0
Note on AP9: Relevant only when Functional Testing estimation is set to m/d
Note on AT10: Relevant only when Functional Testing estimation is set to m/d

## Project Effort
|  |  |  | Front End | [10 empty] | Back End | [19 empty] | QA |  |  | Total per Item
|  |  |  | Angular Screens (with Palmyra UI Studio) |  |  | Native Angular Components (UCs/Screens, widgets) |  |  |  | Components Integration in UI Studio |  |  |  | Screen (SWING) |  |  |  | Screen - UC (GWT Palmyra) |  |  |  | Report |  |  | Process |  |  | Configuration |  |  | Service/Activity |  |  | Functional Testing |  |  |  | Total STD | Total Mkt | Total SPEC
|  |  |  | Simple | Average | Difficult | Simple | Average | Difficult | Complex | Simple | Average | Difficult | Complex | Simple | Average | Difficult | Complex | Simple | Average | Difficult | Complex | Simple | Average | Complex | Simple | Average | Complex | Simple | Average | Complex | Simple | Average | Complex | Simple | Average | Difficult
| Effort per unit |  |  | 0.875 | 2 | 4.5 | 0.9 | 4.7 | 10.7 | 21.9 | 0.78 | 1.5 | 3 | 4.5 | 3.55 | 6.8 | 10 | 17 | 1.02 | 3.48 | 6.48 | 13.68 | 1.02 | 2.52 | 7.68 | 2.4 | 4.8 | 13.2 | 0.6 | 1.2 | 1.8 | 0.9 | 3 | 6 | 0.0625 | 0.125 | 0.375
Owner | # units to develop |  |  | 60 | 12 | 0 | 1 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 22 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 11 | 1 | 0 | 0 | 0
Product | Requirements BRD & BSD (in m/d) | [36 empty] | 0 | 0 | 0 | 0 | Effort stated in m/d depending on the knowledge level and the materials available for the analysis
R&D | Development Effort |  |  | 52.5 | 24 | 0 | 0.9 | 14.1 | 10.7 | 21.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.6 | 55.44 | 46.08 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6 | 33 | 6 | 0 | 0 | 0 | 361.82 | #REF! | #REF! | #REF!
R&D | Dev Management (%dev) |  | 10% | [34 empty] | 36.182 | #REF! | #REF! | #REF!
R&D | Iterations Cost - in Man Days (Retest effort) |  | 0% | [34 empty] | 0 | #REF! | #REF! | #REF!
R&D | Architecture Technique/Fonctionnelle (%dev or in m/d) |  | 10% | [34 empty] | 36.182 | #REF! | #REF! | #REF!
R&D | Benchmarking (%dev or in m/d) |  | 5% | [34 empty] | 18.091 | #REF! | #REF! | #REF!
R&D | Build/Packaging/Plateforme (%dev or in m/d) |  | 5% | [34 empty] | 18.091 | #REF! | #REF! | #REF!
R&D | Code integration in other branches (% dev per branche) |  | 0% | [34 empty] | 0 | #REF! | #REF! | #REF!
R&D | Support & bug fixing - Functional Testing (%dev) |  | 8% | [34 empty] | 28.9456
R&D | Support & bug fixing - End to End Testing (%dev) |  | 6% | [34 empty] | 21.7092
R&D | Support & bug fixing - Validation Testing (%dev) |  | 6% | [34 empty] | 21.7092 | #REF! | #REF! | #REF!
R&D | Functional Testing (%dev or in m/d) |  | 15% | [34 empty] | 54.273 | #REF! | #REF! | #REF!
R&D | Test Campaing-End to End Testing (%dev or in m/d) |  | 20% | [34 empty] | 72.364 | #REF! | #REF! | #REF!
R&D | Automatic Testing (%dev or in m/d) |  | 5% | [34 empty] | 18.091 | #REF! | #REF! | #REF!
Product | Test Campaing-Validation Testing (%dev or in m/d) |  | 15% | [34 empty] | 54.273 | #REF! | #REF! | #REF!
Product | Reviews & follow-up (%dev) |  | 10% | [34 empty] | 36.182 | #REF! | #REF! | #REF!
Product | Product Documentation (%dev) |  | 10% | [34 empty] | 36.182 | #REF! | #REF! | #REF!
| Total Implementation w/o Risk | [36 empty] | 814.095 | #REF! | #REF! | #REF!
| Risk Factors |  | 20% | [34 empty] | 162.819 | #REF! | #REF! | #REF!
| Total Implementation Effort | [36 empty] | 976.914 | #REF! | #REF! | #REF!
| Total Project Effort (Analysis+Implementation) | [36 empty] | 976.914
| Project Duration (months) | [36 empty] | 6.989
R&D Effort Details
| Task Nature | Dev | F° Testing
| Analysis | 82.2 | 0
| Model/Design | 39.95 | 0
| Coding | 68 | 0
| Configuration (Labels, VF,…) | 47.2 | 0
| Unit Test Coding | 63.5 | 0
| Data binding | 14 | 0
| Sub Total - Devs | 314.85 | 0
| Functional Testing | 0 | 0
| Functional Testing - Bugs Fixing | 0 | #REF!
| Sub Total - Functional Testing | 0 | #REF!
| Functional Testing | 0 | 0
| Integration Testing (Execution) | 0 | 0
| Sub Total - QA & testing | 0 | 0
| User Documentation | 46.97 | 0
| Sub Total - Documentation | 46.97 | 0
| Total | 361.82 | #REF!
Estimations breakdown per team
[43 empty] | PH | TSK | PRD | R&D | Total
[43 empty] | ANA |  | 0 | 0 | 0
[43 empty] | IMP |  | 126.637 | 687.458 | 814.095
[44 empty] | DEV | 0 | 314.85 | 314.85
[44 empty] | ARCH | 0 | 36.182 | 36.182
[44 empty] | BNCH | 0 | 18.091 | 18.091
[44 empty] | PACK | 0 | 18.091 | 18.091
[44 empty] | BUG FIXING | 0 | 72.364 | 72.364
[43 empty] | TESTING | END TO END | 0 | 126.637 | 126.637
[43 empty] | TESTING | REG/AUTO |  | 18.091
[43 empty] | TESTING | VALIDATION | 54.273 | 0 | 54.273
[44 empty] | DOC | 36.182 | 46.97 | 83.152
[44 empty] | PM | 36.182 | 36.182
[43 empty] | RISK |  | 25.3274 | 137.4916 | 162.819
[43 empty] | Total |  | 151.9644 | 824.9496 | 976.914
[45 empty] | 15.56% | 84.44% | 100%
Note on B6: - Requirement Specification or Requirements validation workshops with the Delivery team (Including high level Test Cases elaboration) - Training & Marketing Materials (Presentations, Videos,…)
Note on D9: Relevant in the case of devs performed over several sprints (minor likelihood)
Note on B12: Release upgrade (part of the packaging effort) 5 % for Product Projects
Note on D19: Effort based on the elaborated tests scripts
Note on B21: Business & Technical Solution validation. (Daily meetings, clarifications, Devs demos, testing follow-up)
Note on B24: Refer to Percentage per project tasks sheet

## Estimation Matrix
|  |  | Front End | [10 empty] | Back End | [19 empty] | Functional Testing
| Type |  | Angular Screens (with Palmyra UI Studio) |  |  | Native Angular Components (UCs/Screens, widgets) |  |  |  | Components Integration in UI Studio |  |  |  | Screen (SWING) |  |  |  | Screen - UC (GWT Palmyra) |  |  |  | Reports |  |  | Process |  |  | Configuration |  |  | Service/Activity |  |  | Functional Testing
| Complexity Level |  | Simple | Average | Difficult | Simple | Average | Difficult | Complex | Simple | Average | Difficult | Complex | Simple | Average | Difficult | Complex | Simple | Average | Difficult | Complex | Simple | Average | Complex | Simple | Average | Complex | Simple | Average | Complex | Simple | Average | Complex | Simple | Average | Difficult
Item | Formula | %
Analysis | M/D |  | 0.25 | 0.5 | 1.5 | 0.25 | 0.75 | 1 | 3 | 0.15 | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 1 | 2.5 | 0.25 | 0.6 | 1 | 2.5 | 0.25 | 0.6 | 1.5 | 0.5 | 1 | 3 | 0.5 | 1 | 1.5 | 0.25 | 0.5 | 1 | 0 | 0 | 0
Model/Design | M/D |  | 0 | 0 | 0 | 0 | 0.25 | 1.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0.75 | 1.5 | 3 | 0.2 | 0.6 | 1 | 2.5 | 0.2 | 0.6 | 1.5 | 0.5 | 1 | 3 | 0 | 0 | 0 |  | 0.5 | 1 | 0 | 0 | 0
Coding/DB script | M/D |  | 0 | 0 | 1.5 | 0.5 | 1 | 3 | 7 | 0.5 | 1 | 2 | 3 | 2.5 | 4 | 5 | 7 | 0 | 0.8 | 2 | 4 | 0 | 0.5 | 2 | 0.5 | 1 | 3 | 0 | 0 | 0 | 0.25 | 1 | 2 | 0 | 0 | 0
Configuration (i.e UI Studio & Translation for Angular, Labels & VF for GWT,…) | M/D |  | 0.25 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unit Test Automation | M/D |  | 0.25 | 0.5 | 0.5 | 0 | 1.5 | 3 | 4 | 0 | 0 | 0 | 0 | 0.25 | 0.5 | 1 | 2 | 0 | 0.5 | 1 | 2 | 0 |  | 1 | 0.5 | 1 | 2 | 0 | 0 | 0 | 0.25 | 0.5 | 1 | 0 | 0 | 0
Data-Binding | M/D |  | 0.125 | 0.25 | 0.25 | 0 | 0.5 | 0.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Functional Test (Execution) | M/D |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0625 | 0.125 | 0.375
Sub Total - Code writing or Functional Testing |  |  | 0.875 | 2 | 4.5 | 0.75 | 4 | 9 | 18.5 | 0.65 | 1.25 | 2.5 | 4 | 3 | 5.75 | 8.5 | 14.5 | 0.85 | 2.9 | 5.4 | 11.4 | 0.85 | 2.1 | 6.4 | 2 | 4 | 11 | 0.5 | 1 | 1.5 | 0.75 | 2.5 | 5 | 0.0625 | 0.125 | 0.375
R&D Documentation | % of dev | 20% | 0 | 0 | 0 | 0.15 | 0.7 | 1.7 | 3.4 | 0.13 | 0.25 | 0.5 | 0.5 | 0.55 | 1.05 | 1.5 | 2.5 | 0.17 | 0.58 | 1.08 | 2.28 | 0.17 | 0.42 | 1.28 | 0.4 | 0.8 | 2.2 | 0.1 | 0.2 | 0.3 | 0.15 | 0.5 | 1
Sub Total - Devs |  |  | 0 | 0 | 0 | 0.15 | 0.7 | 1.7 | 3.4 | 0.13 | 0.25 | 0.5 | 0.5 | 0.55 | 1.05 | 1.5 | 2.5 | 0.17 | 0.58 | 1.08 | 2.28 | 0.17 | 0.42 | 1.28 | 0.4 | 0.8 | 2.2 | 0.1 | 0.2 | 0.3 | 0.15 | 0.5 | 1 | 0 | 0 | 0
Development Effort |  |  | 0.875 | 2 | 4.5 | 0.9 | 4.7 | 10.7 | 21.9 | 0.78 | 1.5 | 3 | 4.5 | 3.55 | 6.8 | 10 | 17 | 1.02 | 3.48 | 6.48 | 13.68 | 1.02 | 2.52 | 7.68 | 2.4 | 4.8 | 13.2 | 0.6 | 1.2 | 1.8 | 0.9 | 3 | 6 | 0.0625 | 0.125 | 0.375
Risk Ratios | 53.85%
31.58%
42.71%
Note on AC2: IBENMIMOUN: Ca peut être le dashboard, la sécurité, les schémas comptables...
Note on A8: DB script for Soliam Non Angular screes development (Upgrade task)

## Glossary 1 - Complexity Guide
Type | Complexity level | Megara
Screens - UC (GWT - Palmyra) | Simple | Palmyra Default Screen. No additional coding. The effort is related to the UML and its adjustment
| Average | Palmyra Default Screen with maximum 5 changes of the default screen behaviour
| Difficult | Palmyra Default Screen with maximum 10 changes of the default screen behaviour
| Complex | Fully rebuild screen (not default Palmyra) or default Palmyra having: * Multiple controls and/or * Multiple override of default behaviour and/or * Navigation logic complicated with multiple sub-pages
Screen (Swing SF) | Simple | - Screen containing 5 fields and/or - 1 action (search,...) and - not including data controls and - not containing sub-pages/screens (Search screen,...)
| Average | - Screen containing 10 fields and/or - more than 1 action (search, export…) and/or - including data controls and - not containing sub-pages/screens (Manual creation screen,...)
| Difficult | - Screen containing more than 10 fields and/or - more than 1 action (search, export…) and/or - including data controls and/or - containing sub-pages/screens (Manual creation screen,...)
| Complexe | - Screen containing more than 10 fields and/or - more than 1 action (search, export…) and/or - including data controls and/or - special behaviour (conditional view based on data) and/or - containing sub-pages/screens (Unitary Order manual creation,...)
Angular Screens (with Palmyra UI Studio) | Simple | Screen generated by Palmyra UI Studio with at most 10 fields, this concerns CRUDs only (Currency, Country,…)(Currency, Country,…)
| Average | Screen generated by Palmyra UI Studio with up to 10 fields and changes to Palmyra's UI default behavior. Custom configuration of presentation logic (Eg: Read only condition, Navigation, on Blue events,….)
| Difficult | - Screen generated by Palmyra UI Studio with at most 10 fields. Requiring additional development in native Angular (Eg: Modification of the HTML output of UI Studio).
Native Angular Components (UCs/Screens, widgets) | Simple | - Use of an existing component on the market (Eg: integration of a simple component (calendar) PrimeNG or other, in a screen)
| Average | - Override/Customization of the behavior of an existing component (Example: double scale chart, Table, Pie chart ...) or - Development of a new unitary and display component (selector or card) which does not present any interactions with other components.
| Difficult | - Development of a new component based on several other components without navigation behavior (Example: Inverted table) involving a change of state or - Development of a new component which presents a high level of interaction with other components and / or with the back end (Eg: grad & drop ...)
| Complex | - Development of a new component which offers navigation behavior and interaction with several components (Example: Wizard, Dashboard as container ...) - Between 3 and 5 states - 2 complex GUI events (Eg: drag & drop, scroll ...) - 2 interactions with other graphics components - Between 3 and 5 interactions with the services
Components Integration in UI Studio | Simple | Simple component integration
| Average | Average component integration
| Difficult | Difficult component integration
| Complex | Complex component integration
Report | Simple | No effort to prepare the data to display. The workload is the design of iReport
| Average | Average effort to prepare the data to display.
| Complex | Important effort to prepare the data: * Read from multiple tables and/or * Grouping, totals, sub-totals and/or * caulcation to be done.
Process | Simple | Workflow design with maximum 6 statuses
| Average | Workflow design with max 12 statuses
| Complex | Workflow complicated with more than 12 statuses, with conditional actions
Configuration | Simple | Easy configuration (labels, straight-thourgh mapping…) with small effort of test
| Average | Configuration that requires tests (SLA, conditional behaviour …)
| Complex | Complicated configuration (mapping with sub-mapping, mapping with conditions, security configuration…) with a large scope of testing
Service/ Activity | Simple | Method or service to develop with easy algorithm (validation of ISIN algorithm)
| Average | Method or service to develop with an alogorithm average (commission calculation using scales)
| Complex | Method or service with complex algorithm (requires different data, requires optimisation, impacting the memory usage, critical for performance …): example of allocating market instruction to multiple client instructions.
Funtional Testing | Simple | Test case with testing duration not exceeding 0,5hr
| Average | Test case with testing duration between 0,5hr and 1hr
| Difficult | Test case with testing duration between 1hr and 3hrs

## Glossary 2 - Project Tasks
Item | Definition
Requirements BRD & BSD (in m/d) | Effort related to the analysis and the elaboration effort of the Requirements documents
Development Effort | Development phase effort : Design, coding, Unit tests
Dev Management (%dev) | Management effort for the dev. phase : Development follow up, meetings, resources management, progress reports, …
Iterations Cost - in Man Days (Retest effort) | Iteration cost in case of intermediate deliveries in the development phase. This workload encompasses packaging, delivery and support of the delivery
Architecture Technique/Fonctionnelle (%dev or in m/d) | Definition of the technical and functional architecture and its documentation.
Benchmarking (%dev or in m/d) | Optimization of screens and processes and tuning if necessary
Build/Packaging/Plateforme (%dev or in m/d) | Build, Maintenance of databases, Versionning,...
Code integration in other branches (% dev per branche) | Effort relevant when it is required to integrate a code from an other Branch (example: integrate a functionnality originally developed on the client support branch to the Tunck…).
Functional Testing (%dev or in m/d) | Test of developped functions
Support & bug fixing - Functional Testing (%dev) | Bug fixing related to the developed function
Test Campaing-End to End Testing (%dev or in m/d) | Test of the functions between components, to make sure that the function has the expected impact and behaviour. This includes the regression testing if necessaary (example: interference with functionalities already delivered and tested, change of an existing functionality,…)
Support & bug fixing - End to End Testing (%dev) | Support effort related to the R&D Team End To End Testing
Automatic Testing (%dev or in m/d) | Elaboration effort of the automatic test scripts
Test Campaing-Validation Testing (%dev or in m/d) | These are tests performed by the Product Team after receiving the application developed and tested by R&D team including the regression testing if necessaary.
Support & bug fixing - Validation Testing (%dev) | Support effort related to the Product Team Validation Testing
Reviews & follow-up (%dev) | Product Team follow up effort, meetings, resources management, progress reports, …
Product Documentation (%dev) | Product Team Documentation effort: - Functional Guide review - Commercial documentation - Release note...
Risk Factors | The risk factor reflects the quality of client user requirements / specifications. More specs are detailed risk factor is reduced. It's varies depending on the project phase.
Project Duration (months) | The theoretical duration of the development phase in relation to the workload calculated: This is the square root of (N JH/20)
Estimation Matrix
Development Effort Sub-items
Items | Definition
Analysis | Analysis of User Requirements
Model Design | Design of UML (Diagram Class, Lifecycle …) Angular: Effort related to the design and definition of the UML model - Angular Screen: Not Relevant - Angular Component: Technical design relating to integration with other systems
Coding/DB script | Coding effort or DB script elaboration effort
Configuration | Configuration (i.e UI Studio & Translation for Angular, Labels & VF for GWT,…)
Unit Test Automation | Unit Test Automation
Data-Binding | Data-Binding
R&D Documentation | Effort for the Processing Guide update - Design Doc - Configuration Guide - Functionnalities catalog
Functional Testing Effort
Items | Definition
Functional Test (Execution) | Execution effort related to the developped functions. This section is onlu relevant when the Functional Testing effort estimation is set to m/d

## Percentages
Project phase | Risk rate
RFI/ Expert opinion Phase | 50%
RFP Phase | 30%
Scoping phase | 20%
Sevices (Plamyra) | 29%
R&D project phases | 0%